## Sheet1
DESIGN DEVELOPMENT ROADMAP
PROJECT NAME
PROJECT NO. |  |  |  |  | PIC:
DATE |  |  |  |  | PM:
PA/AC:
INSTRUCTION NOTES
1. Refer to Responsibility Key below. Team shall assign responsibilities for tasks listed below.
2. Tasks listed below are not necessarily in cronological order in which they need to be performed/completed.
3. Not all tasks are applicable. If not applicable to project or phase, denote in Remark Column.
4. Enter date that the task is completed.
5. Person responsible shall initial task, confirming that task has been completed.
RESPONSIBILITY KEY
1:Primary Responsibility 2:Secondary Responsibility 3:Support
TASK | PIC | PM | PA | OTHER | DATE COMPLETE | INTL. | REMARK/REFERENCE
Meet with City Planning Dept. as Required with Owner
D.D.Deliverable List
List of Owner Furnished FF&E
DD Minimun Drawing Requirements | [6 empty] | Refer to Drawings Checklist
Prepare necessary documents to include: (Check required submittal documents in Owner/Architect contract)
Life safety plan
Verify wall types (Fire, Sound and Plumbing)
Room Data Sheets
Specifications Meeting
Develop Specifications Including front end for Owner
Further Define Building Systems
Periodically review internal office budgets and production schedules; compare with actual progress.
Review and update project schedule and staffing needs
As documents develop, confer with and obtain preliminary review from regulatory agencies such as:
Building department
Fire Marshal (State & Local)
Dept. of Health
Dept. of Education
Zoning Commission
Planning Commission
Design Review Board
Other:
Identify all documents with project number and date.
Obtain Owner’s approval of expenditures for any models, perspectives or renderings required for the project.
Review the building design program and verify compliance.
Re-check Schematic Design documents for code compliance.
Obtain Owner’s approval in the event that additional consultants are required.
Receive results of all investigations and tests, including soil borings and analysis. If necessary, request additional information. Forward final information to appropriate consultants.
Review all other data received from the Owner and consultants. If necessary, request additional data.
In consultation with the Owner and consultants, develop a checklist of special systems.
Define actual occupancy for each area, check against program and building code review, forward to consultants.
Update Fire & ADA code review, verify compliance, and make alterations necessary.
Prepare other necessary documents to include: (Check required submittal documents in Owner/Architect contract)
Life safety plan
Floor plans w/ furniture
Verify wall types (Fire, Sound and Plumbing)
Exterior elevations w/ materials indicated and noted
Building sections trans and longitudinal
Wall section typical noted
Finish schedule
Renderings
Specifications – Including front end for Owner review
Prepare area calculations (net and gross)
Prepare building volume calculations.
Prepare a preliminary Project Manual.
Update materials, equipment, fixtures and building systems file.
Direct consultants to prepare design documents as required to illustrate and describe their portions of the project.
Require all consultants to produce their design documents following the same format as the architectural drawings.
Conduct one or more group coordination meetings with consultants.
Reach agreement on structural, mechanical, electrical, and other building systems.
Confirm that the selected engineering and construction systems are compatible.
Prepare area calculations (net and gross).
Review all other data received from the Owner and consultants. If necessary, request additional data.
Prepare estimate of probable construction cost based on all available data. Include appropriate contingency to cover future development of the project. If requested by Owner, provide a detailed estimate and/or life cycle costing as additional service.
Submit Design Development documents to the Owner. (These documents may include, but may not be limited to, drawings, descriptions, calculations, outline specifications, colors, materials and statements of probable construction cost. Verify exact documents required in Owner/Architect contract.
Plan appropriate presentation media, optional design features if necessary
Review meeting with Owner at the BIM Lab
Obtain Owner’s written approval of Design Development documents, and direction to proceed into Construction Documents.
Notify accounting of phase change.